WILEY UNIVERSITY
INSTITUTIONAL REVIEW BOARD (IRB)
IMPLEMENTATION PLAN OF ACTION

Office of Institutional Research and Effectiveness
February 2026

# Table of Contents

1. Phase 0: Get the Green Light

2. Phase 1: Chair & FWA Registration

3. Phase 2: Committee & Policies

4. Phase 3: Infrastructure & Training

5. Phase 4: Launch

6. Minimum Requirements for Launch

7. Key Contacts & Resources

8. Estimated Budget (Year 1)

9. Top Risks

# Phase 0: Get the Green Light (This Week)

These are blockers — nothing else moves until these are done.

## Step 1: Obtain President's Written Authorization

Secure a signed letter or memo from the University President endorsing the creation of the IRB. This document will be required for the FWA application and serves as the institutional commitment to human subjects protection.

Deliverable: Signed presidential authorization letter

## Step 2: Secure Budget Approval

The recommended Year 1 budget is $15,000–$25,000. At minimum, secure the low-end estimate of $7,000. Key cost items include:

CITI Program subscription

IRB Chair stipend

Community member honorarium

Optional IRB management software

Training materials and supplies

Deliverable: Approved budget allocation memo

## Step 3: Make 6 Key Decisions

Sit down with institutional leadership and resolve the following decisions. These will shape every policy, form, and workflow that follows.

| Decision | Options |
| --- | --- |
| FWA Scope | Voluntary compliance vs. required for federal funding? |
| Review Authority | All research vs. only funded/published research? |
| Student Research | Full review vs. expedited track for student projects? |
| Member Compensation | Stipends vs. service expectation? |
| Technology | Manual/forms-based start vs. platform investment (e.g., IRBNet, Cayuse)? |
| Staffing | Assign existing staff vs. hire a dedicated IRB coordinator? |

Deliverable: Completed decision matrix signed by leadership

# Phase 1: Chair & FWA Registration (Weeks 1–2)

## Step 4: Identify and Recruit an IRB Chair

The Chair should ideally have research ethics experience or a strong research background. This person will lead committee meetings, oversee protocol reviews, and serve as the primary signatory on IRB decisions.

Deliverable: Confirmed IRB Chair with signed appointment letter

## Step 5: Enroll Chair in CITI Training

The Chair must complete CITI (Collaborative Institutional Training Initiative) certification before the IRB can operate. Enroll them immediately as this can take 1–2 weeks to complete. Register at https://about.citiprogram.org

Deliverable: Chair's CITI certification completion certificate

## Step 6: Submit FWA Application

The Federalwide Assurance (FWA) application is submitted to the Office for Human Research Protections (OHRP) at https://www.hhs.gov/ohrp. This is the CRITICAL PATH item — approval typically takes 4–6 weeks, so submit as early as possible.

FWA application requires:

Institutional authorization (Step 1)

Designated IRB Chair information

Assurance of compliance with 45 CFR 46 (Common Rule)

Description of the IRB composition plan

Deliverable: FWA application confirmation/tracking number from OHRP

## Step 7: Draft Committee Recruitment List

Federal regulations (45 CFR 46.107) require at least 5 members with the following composition:

At least 1 member whose primary expertise is in a scientific area

At least 1 member whose primary expertise is in a non-scientific area

At least 1 member who is not affiliated with the institution (community member)

Diversity in race, gender, cultural background, and sensitivity to community attitudes

Deliverable: List of 7–10 potential members with contact info and expertise areas

# Phase 2: Committee & Policies (Weeks 2–3)

## Step 8: Recruit and Confirm Committee Members

Formally invite members from the recruitment list. Provide each with an appointment letter outlining their role, term length, meeting expectations, and any compensation. The community member may be the hardest to recruit — consider local clergy, community leaders, or retired professionals.

Deliverable: Signed appointment letters from all 5+ committee members

## Step 9: Draft Core Policies (3 Minimum)

The following policies are required before the IRB can operate:

### Review Categories Policy

Define the three review levels: Exempt, Expedited, and Full Board review. Include criteria for each category per 45 CFR 46.104 and 46.110.

### Conflict of Interest (COI) Policy

Address how conflicts are identified, disclosed, and managed. This is especially critical at a small institution where faculty may review colleagues' work.

### Adverse Events / Unanticipated Problems Policy

Define reporting requirements, timelines, and response procedures for adverse events or unanticipated problems involving risk to subjects.

Deliverable: Three approved policy documents

## Step 10: Create Protocol Submission Form

This is the primary application form that researchers will complete to request IRB review. It should capture: project title, PI information, funding source, research design, subject population, risks/benefits, informed consent process, and data security plan.

Deliverable: Finalized IRB Protocol Submission Form

## Step 11: Create Informed Consent Template

Provide researchers with a standardized consent template that meets the requirements of 45 CFR 46.116. Include all required and applicable additional elements of consent.

Deliverable: Informed Consent Document Template

# Phase 3: Infrastructure & Training (Weeks 3–4)

## Step 12: Define the Review Workflow

Map the complete lifecycle of a protocol submission from intake to final decision. Include: submission receipt, administrative pre-review, category determination, reviewer assignment, review process, decision notification, and appeals process.

Deliverable: Review workflow diagram and written procedures

## Step 13: Set Up Recordkeeping System

Establish a secure, organized system for maintaining all IRB records. Federal regulations require records to be retained for at least 3 years after study completion. Even a well-structured SharePoint or shared drive folder system works to start.

Required records include:

Protocol submissions and all revisions

IRB meeting minutes

Correspondence with researchers

Approval/disapproval letters

Adverse event reports

Member rosters and training records

Deliverable: Organized folder structure with naming conventions documented

## Step 14: Enroll All Committee Members in CITI Training

All IRB members should complete relevant CITI modules. At minimum, members should complete the IRB Members module and the Human Subjects Research (HSR) module.

Deliverable: CITI completion certificates for all committee members

## Step 15: Build Researcher-Facing Web Presence

Create a webpage or site that serves as the central hub for researchers. This should include: training requirements, downloadable forms, submission instructions, FAQs, meeting schedule, and contact information. This can be hosted on an existing Wiley platform or a Netlify site.

Deliverable: Published IRB website with all forms and instructions

## Step 16: Conduct a Mock Review

Before going live, run the full committee through a mock protocol review. Use a fictional or sample protocol to test: the submission form, the review workflow, committee discussion process, and decision documentation. This builds confidence and identifies gaps in your process.

Deliverable: Completed mock review with documented lessons learned

# Phase 4: Launch (Weeks 5–6)

## Step 17: Soft Launch

Accept the first 1–2 real protocol submissions. Walk them through the full process with extra care and attention. Use these initial submissions to refine your workflow before opening to the full campus.

## Step 18: Hold First Official IRB Meeting

Convene the full board for the first official meeting. Establish meeting norms, review the first protocols, and document meeting minutes per federal requirements.

## Step 19: Publish Researcher Training Requirements

Announce campus-wide that all research involving human subjects now requires IRB review. Publish the training requirements (typically CITI certification) and deadlines for compliance.

## Step 20: Full Operations

Open the IRB for all submissions. Establish a regular meeting cadence (monthly recommended to start). Monitor workload and adjust processes as needed.

Phase 4 Deliverables: Operational IRB with documented first meeting minutes and approval letters

# Minimum Requirements for Launch

FWA application submitted to OHRP

5+ committee members (including non-scientist & community member)

CITI-certified Chair

Basic policies (review categories, COI, adverse events)

Protocol submission forms & consent template

Defined review workflow

Recordkeeping system

Published researcher training requirements

# Key Contacts & Resources

| Resource | URL / Reference |
| --- | --- |
| OHRP (FWA Registration) | https://www.hhs.gov/ohrp |
| CITI Program | https://about.citiprogram.org |
| PRIM&R | https://primr.org |
| Common Rule | 45 CFR 46 |

# Estimated Budget (Year 1)

| Item | Low Estimate | High Estimate |
| --- | --- | --- |
| CITI Subscription | $1,500 | $3,000 |
| Chair Stipend | $2,000 | $5,000 |
| Community Member Honorarium | $500 | $2,000 |
| IRB Software (optional) | $0 | $5,000 |
| Training & Supplies | $1,000 | $3,000 |
| Miscellaneous | $2,000 | $4,000 |
| TOTAL | $7,000 | $22,000 |

# Top Risks

FWA approval delay (4–6 weeks typical)

Community member recruitment difficulty

Faculty resistance to oversight

Small campus conflict of interest issues

Student thesis volume overwhelming capacity